## README
DOC-003 — Product Backlog
REM Waste — Booking Flow Platform · Version 1.0
Document ID | DOC-003
Title | Product Backlog — Source of Truth
Project | REM Waste Booking Flow Platform
Version | 1.0
Status | Approved
Author | Evgenii Subbotin
Date | 2026-04-16
References | DOC-001 · DOC-002 · DOC-005
Sheet Guide
Sheet | Contents | Primary Audience
US Backlog | All User Stories: functional, technical, documentation tasks. MoSCoW priority, WSJF, Acceptance Criteria, status. | PM / EM / Dev
WBS — Functional | Work Breakdown by user journey step (Step 1 → Step 4 + cross-cutting). Deliverable-oriented. | PM / Dev
WBS — Architecture | Work Breakdown by system layer (Frontend / API / DevOps / QA / Docs). Effort-oriented. | Tech Lead / EM
DoR & DoD | Definition of Ready checklist per US. Definition of Done checklist per US. Quality gates. | All
Sprint Plan | 5-day sprint plan: which US delivered each day, sequencing rationale, dependencies. | PM / EM
README | This page. | All
MoSCoW Legend
Must | Non-negotiable. Assessment fails without this. All Must items = MVP.
Should | Important, high value. Deliver if time permits. Skipping is a known trade-off.
Could | Nice to have. Deliver only after all Must and Should are done.
Won't | Explicitly out of scope for this iteration. Acknowledged, not forgotten.

## US Backlog
WSJF = (BV+TC+RR) / JS
ID | Title | Type | MoSCoW | BV (1-10) | TC (1-10) | RR (1-10) | JS (1-10) | WSJF | Day | Status | Acceptance Criteria | Notes / References
STEP 1 — POSTCODE LOOKUP & ADDRESS SELECTION
US-001 | Postcode input field with UK format validation | Functional | Must | 9 | 9 | 8 | 2 |  | 1 | To Do | Given user enters valid UK postcode → form accepts it Given invalid format (12345, empty, too short) → inline error shown Given XSS/SQL injection input → rejected with 400, no execution | GL-D-008. Regex: ^[A-Z]{1,2}[0-9][0-9A-Z]?\s[0-9][A-Z]{2}$
US-002 | POST /api/postcode/lookup — happy path (SW1A 1AA) | Functional | Must | 10 | 10 | 9 | 1 |  | 1 | To Do | Given SW1A 1AA → returns 200 + array of 12+ addresses Given response → each address has id, line1, city fields Given response → displayed in dropdown for user selection | API contract: DOC-001 GL-D-009. Fixture: GL-D-015
US-003 | Address selection from dropdown after lookup | Functional | Must | 9 | 8 | 7 | 2 |  | 1 | To Do | Given addresses returned → user can select one from list Given selection → address stored in booking state Given selection → 'Continue' button activates | Selected address ID passed to POST /api/booking/confirm as addressId
US-004 | Empty state — EC1A 1BB returns 0 addresses | Functional | Must | 8 | 9 | 8 | 2 |  | 1 | To Do | Given EC1A 1BB postcode → API returns empty addresses array Given empty state → 'No addresses found' message shown Given empty state → manual entry form revealed automatically | GL-D-010. Manual entry: line1, city, postcode fields minimum
US-005 | Loading state — M1 1AE simulated latency | Functional | Must | 7 | 8 | 7 | 1 |  | 1 | To Do | Given M1 1AE postcode → loading spinner/skeleton shown during 1500ms delay Given loading → form inputs disabled to prevent double submit Given response arrives → loading state clears, addresses shown | Latency: 1500ms. Loading indicator must be visible to user.
US-006 | Error state + retry — BS1 4DJ 500 on first call | Functional | Must | 9 | 9 | 9 | 2 |  | 1 | To Do | Given BS1 4DJ → first call returns 500 error Given error → error message shown with 'Try again' button Given retry click → second call returns 200 with addresses Given retry → error state clears, addresses displayed | BS1 4DJ fixture: 500 first, 200 second. Tests: TC-016–019
US-007 | Manual address entry fallback | Functional | Must | 7 | 7 | 6 | 2 |  | 1 | To Do | Given manual entry form → user can type line1, line2 (optional), city, postcode Given manual entry → all required fields validated before Continue Given complete manual entry → stored in booking state same as selected address | Required: line1, city, postcode. Optional: line2
STEP 2 — WASTE TYPE SELECTION
US-008 | Waste type selection — General, Heavy, Plasterboard | Functional | Must | 10 | 10 | 9 | 2 |  | 2 | To Do | Given Step 2 → three waste types displayed: General, Heavy, Plasterboard Given General selected → no additional options, Continue available Given Heavy selected → no additional options, Continue available; heavyWaste:true sent to API Given Plasterboard selected → plasterboard option selector appears | GL-D-004, GL-D-005, GL-D-006. POST /api/waste-types on Continue
US-009 | Plasterboard branching — 3 handling options | Functional | Must | 10 | 9 | 10 | 3 |  | 2 | To Do | Given Plasterboard selected → 3 options shown: Separate bag / Dedicated skip / Licensed carrier Given no option selected → Continue disabled Given option selected → stored as plasterboardOption in state Given Continue → POST /api/waste-types with plasterboard:true + plasterboardOption | GL-D-007. This is the key branching test — at least 1 bug must relate to this flow (assessment req)
US-010 | POST /api/waste-types API call on Step 2 continue | Functional | Must | 8 | 8 | 7 | 1 |  | 2 | To Do | Given any valid waste type selection → POST /api/waste-types fires on Continue Given valid payload → 200 ok received → proceed to Step 3 Given API failure → error shown with retry | Payload: {heavyWaste, plasterboard, plasterboardOption}. GL-T-021
STEP 3 — SKIP SELECTION
US-011 | GET /api/skips — fetch skip options with postcode + heavyWaste | Functional | Must | 10 | 9 | 9 | 1 |  | 2 | To Do | Given entering Step 3 → GET /api/skips?postcode=&heavyWaste= fires automatically Given response → 8+ skip options returned Given heavyWaste:true → at least 2 larger skips have disabled:true Given heavyWaste:false → all skips enabled | GL-D-003, GL-D-013. Query params: postcode (normalised, no space) + heavyWaste boolean
US-012 | Skip grid display — enabled and disabled states | Functional | Must | 9 | 9 | 8 | 2 |  | 2 | To Do | Given skip options loaded → displayed as grid/list with size, price, availability Given disabled skip → greyed out, not selectable, reason shown (e.g. 'Not suitable for heavy waste') Given enabled skip → selectable, highlights on selection Given selection → price shown, Continue activates | GL-D-013. Visual distinction required. Screenshot evidence needed for assessment
US-013 | Skip selection state persistence | Functional | Must | 7 | 7 | 6 | 1 |  | 2 | To Do | Given skip selected → size and price stored in booking state Given user navigates back to Step 2 and returns → selection cleared (fresh state) Given skip selected → price shown in summary widget | State management: React useState or equivalent
STEP 4 — REVIEW, PRICE BREAKDOWN & CONFIRM
US-014 | Review step — full booking summary display | Functional | Must | 10 | 9 | 8 | 2 |  | 3 | To Do | Given Step 4 → all selected values shown: address, waste type, plasterboard option (if applicable), skip size Given review → price breakdown shown: base price, any surcharges, total Given review → all values match what user selected in Steps 1–3 | GL-D-011. Price breakdown is mandatory per assessment spec
US-015 | POST /api/booking/confirm — successful booking | Functional | Must | 10 | 10 | 10 | 2 |  | 3 | To Do | Given all fields complete → Confirm button active Given Confirm clicked → POST /api/booking/confirm fires once Given 200 response → bookingId shown on success screen Given success → no further submission possible | Response: {status:'success', bookingId:'BK-XXXXX'}. Double-submit prevention mandatory
US-016 | Double-submit prevention | Functional | Must | 9 | 10 | 9 | 1 |  | 3 | To Do | Given Confirm clicked → button disabled immediately Given loading state → spinner shown, button not clickable Given rapid double-click → only ONE POST /api/booking/confirm fired Given success → button remains disabled | NFR-006. Verify via Playwright request intercept count assertion
US-017 | Booking confirmation success screen | Functional | Must | 8 | 7 | 6 | 1 |  | 3 | To Do | Given successful booking → success screen shown with bookingId Given success screen → clear visual confirmation (not just a toast) Given success screen → no 'back' path to re-submit | BookingId format: BK-XXXXX per API contract
CROSS-CUTTING — UI/UX & STATE MANAGEMENT
US-018 | Multi-step wizard navigation — forward and back | Functional | Must | 8 | 8 | 7 | 2 |  | 2 | To Do | Given any step → user can navigate back to previous step Given back navigation → previous step data preserved in state Given back from Step 3 → waste type selection still shown Given browser back button → handled gracefully (no broken state) | State must persist across step navigation. Back button edge case: test separately
US-019 | Step progress indicator | Functional | Should | 5 | 4 | 3 | 1 |  | 3 | To Do | Given any step → progress indicator shows current step (1/4, 2/4 etc) Given completed step → visually marked as done Given future step → visually marked as upcoming | Not in assessment spec but expected for realistic booking UX
US-020 | Mobile responsive layout — 375px viewport | Functional | Must | 8 | 9 | 7 | 2 |  | 3 | To Do | Given 375px viewport → all steps fully usable without horizontal scroll Given touch targets → all buttons/inputs ≥ 44×44px Given mobile → no content clipped or hidden | NFR-004, NFR-005. Playwright mobile viewport test. Screenshot required for assessment
TECHNICAL — INFRASTRUCTURE & DEVOPS
US-T-001 | Next.js 14 project scaffold + TypeScript config | Technical | Must | 10 | 10 | 10 | 1 |  | 1 | To Do | Given project init → next.config.js, tsconfig.json, tailwind.config.js configured Given tsc --noEmit → zero errors on clean scaffold Given npm run dev → app starts on localhost:3000 | ADR-001. npx create-next-app@latest with TypeScript + Tailwind options
US-T-002 | GitHub repository + branch strategy | Technical | Must | 8 | 7 | 8 | 1 |  | 1 | To Do | Given repo created → main branch protected Given feature work → feature/US-XXX branch naming convention Given PR → requires CI pass before merge Given merge → triggers Vercel production deployment | ADR-003. Branch naming: feature/US-001, fix/BUG-001
US-T-003 | GitHub Actions CI/CD pipeline | Technical | Must | 9 | 9 | 9 | 2 |  | 1 | To Do | Given PR opened → workflow runs: checkout → npm ci → tsc → playwright install → playwright test @smoke Given TypeScript error → pipeline fails at step 3, PR blocked Given test failure → pipeline fails, PR blocked Given all pass → PR mergeable, Vercel preview URL posted | ADR-003. File: .github/workflows/playwright.yml. GL-T-017
US-T-004 | Vercel deployment + environment variables | Technical | Must | 9 | 8 | 8 | 1 |  | 1 | To Do | Given merge to main → Vercel deploys production automatically Given PR → Vercel creates preview URL automatically Given production URL → accessible without login, VPN, or expiry Given BASE_URL env var → accessible in Next.js as process.env.NEXT_PUBLIC_BASE_URL | ADR-002. Assessment requires public URL. Connect GitHub repo in Vercel dashboard
US-T-005 | GitHub Projects board setup | Technical | Must | 5 | 4 | 4 | 1 |  | 1 | To Do | Given GitHub Projects board → all US-XXX items added as cards Given board → MoSCoW field configured Given board → Status field: To Do / In Progress / Done / Deferred Given card → links to this backlog row via ID | ADR-003. Public board for portfolio visibility. ~30 min setup
US-T-006 | In-memory API fixtures — all 4 postcode cases | Technical | Must | 10 | 10 | 9 | 2 |  | 1 | To Do | Given SW1A 1AA → 12 addresses returned Given EC1A 1BB → empty array returned Given M1 1AE → response after 1500ms delay Given BS1 4DJ → 500 on first call, 200 on second (per-request counter) Given any other postcode → 404 or empty | GL-D-015, GL-T-009. Counter for BS1 4DJ must reset between test runs
US-T-007 | In-memory skip fixtures — 8+ options, mixed enabled/disabled | Technical | Must | 9 | 9 | 8 | 2 |  | 1 | To Do | Given heavyWaste:false → all 8 skip sizes enabled Given heavyWaste:true → 12yd and 14yd disabled:true at minimum Given any request → prices consistent with review step display | GL-D-003, GL-D-013. Sizes: 2yd, 4yd, 6yd, 8yd, 10yd, 12yd, 14yd, 16yd
US-T-008 | Playwright framework + test suite setup | Technical | Must | 9 | 9 | 9 | 2 |  | 1 | To Do | Given playwright.config.ts → chromium + webkit projects configured Given Page Object Model → BasePage abstract + page-specific classes Given fixtures/testData.ts → all deterministic test data centralised Given npm test → full suite runs and produces HTML report | ADR-004. Re-use qa-automation-framework patterns from existing portfolio
QA DELIVERABLES — ASSESSMENT REQUIREMENTS
US-Q-001 | Manual test cases — 35+ in markdown table | QA | Must | 10 | 10 | 10 | 3 |  | 5 | To Do | Given manual-tests.md → strict markdown table format Given table → columns: TC-ID, Title, Preconditions, Steps, Expected Result, Actual Result, Status, Priority Given coverage → 10+ negative, 6+ edge case, 4+ API failure, 4+ state transition tests | Assessment requirement. File: docs/manual-tests.md in repo root
US-Q-002 | Playwright E2E — General waste booking flow | QA | Must | 10 | 10 | 9 | 2 |  | 4 | To Do | Given E2E test 1 → completes full flow: SW1A 1AA → General waste → 6yd skip → review → confirm Given each step → assertion on correct UI state Given confirm → bookingId visible in success screen Given CI → test passes on chromium headless | ADR-004. Tagged @smoke. Stable selectors via data-testid attributes
US-Q-003 | Playwright E2E — Heavy waste booking flow | QA | Must | 10 | 10 | 9 | 2 |  | 4 | To Do | Given E2E test 2 → SW1A 1AA → Heavy waste → skip selection shows disabled 12yd/14yd → select 8yd → confirm Given disabled skips → assertion that 12yd and 14yd are not selectable Given CI → test passes on chromium headless | ADR-004. Tagged @smoke. heavyWaste:true in API payload verified
US-Q-004 | Playwright API tests — all 4 endpoints | QA | Must | 9 | 9 | 8 | 2 |  | 4 | To Do | Given API tests → cover all 4 endpoints Given each endpoint → happy path (2xx) + at least 2 negative cases (4xx) Given BS1 4DJ → retry logic tested via API directly Given schema validation → response body fields and types asserted | ADR-004. APIRequestContext. Tagged @regression
US-Q-005 | Bug reports — 3+ with branching/state bug | QA | Must | 8 | 8 | 8 | 2 |  | 5 | To Do | Given bug-reports.md → minimum 3 bugs documented Given each bug → severity, priority, environment, steps to reproduce, actual vs expected, evidence (screenshot) Given at least 1 bug → involves plasterboard branching or state transition | Assessment requirement. If no real bugs found during development — create intentional bug in a branch, document, then fix
US-Q-006 | Accessibility check — WCAG 2.1 AA via axe-core | QA | Must | 8 | 8 | 8 | 2 |  | 4 | To Do | Given axe-core scan on each step → zero critical or serious violations Given all form inputs → have associated labels Given keyboard navigation → all interactive elements reachable via Tab Given Lighthouse accessibility score → ≥ 90 | NFR-003. @axe-core/playwright. Lighthouse CLI or DevTools
US-Q-007 | UI screenshots — assessment evidence package | QA | Must | 7 | 7 | 6 | 2 |  | 4 | To Do | Given ui/ directory in repo → contains: desktop screenshots of each step, mobile (375px) screenshots, error state screenshot, disabled skip screenshot, price breakdown screenshot Given flow video → 60–120 seconds demonstrating complete booking | Assessment requirement: mobile AND desktop. Video can be Loom or screen record
US-Q-008 | Lighthouse report — Performance ≥ 85, A11y ≥ 90 | QA | Must | 8 | 8 | 7 | 1 |  | 4 | To Do | Given Lighthouse run on production URL → Performance score ≥ 85 Given Lighthouse → Accessibility score ≥ 90 Given Lighthouse → report saved as evidence (screenshot or HTML export) | NFR-001, NFR-009. Run against Vercel production URL, not localhost
US-Q-009 | Exploratory testing session — booking flow charter | QA | Should | 6 | 6 | 5 | 2 |  | 5 | To Do | Given charter: 'Explore plasterboard branching and state transitions to find defects automation misses' Given session → heuristics applied: CRUD, Interruptions, State, Boundary Given session → findings documented in exploratory session template | GL-P-018. ~45 min session post-build. Documents automation gaps
DOCUMENTATION — PROJECT LIBRARY ARTEFACTS
US-D-001 | README.md — primary submission document | Documentation | Must | 8 | 7 | 8 | 2 |  | 5 | To Do | Given README.md in repo root → contains: public demo URL, GitHub repo link, project library link Given README → mocking/test data strategy explained Given README → how to run tests locally (npm install, npm test) Given README → links to all DOC-XXX artefacts | Assessment requirement. Entry point for evaluator
US-D-002 | DOC-001 Project Glossary | Documentation | Must | 5 | 4 | 5 | 1 |  | 1 | Done | Given DOC-001 → all domain, technical, and process terms defined Given other documents → use GL-XXX references for precision | ✅ Complete
US-D-003 | DOC-002 Project Charter | Documentation | Must | 6 | 5 | 6 | 1 |  | 1 | Done | Given DOC-002 → scope, objectives, risks, stakeholders, timeline defined Given Charter → all Must Have items traceable to assessment PDF | ✅ Complete
US-D-004 | DOC-003 Product Backlog (this document) | Documentation | Must | 7 | 6 | 7 | 2 |  | 1 | Done | Given DOC-003 → all US-XXX items with MoSCoW, WSJF, AC, status Given Backlog → source of truth for scope, DoR, DoD, sprint plan | ✅ Complete — this document
US-D-005 | DOC-004 ADR Collection | Documentation | Must | 6 | 5 | 6 | 1 |  | 1 | Done | Given DOC-004 → ADR-001 through ADR-006 approved Given each ADR → options compared, decision recorded, consequences acknowledged | ✅ Complete
US-D-006 | DOC-005 Test Strategy | Documentation | Must | 7 | 7 | 7 | 1 |  | 1 | Done | Given DOC-005 → testing pyramid, risk prioritisation, NFR, CI/CD gates, defect management defined | ✅ Complete
US-D-007 | DOC-006 Release Management Plan | Documentation | Must | 6 | 5 | 6 | 1 |  | 1 | To Do | Given DOC-006 → branching strategy, environment map, release checklist, rollback SOP Given plan → consistent with ADR-002 and ADR-003 | Next to generate
US-D-008 | DOC-007 Tech Stack Evaluation | Documentation | Must | 5 | 4 | 5 | 1 |  | 1 | Done | Given DOC-007 → scored matrices for all stack layers, narrative justifications | ✅ Complete
US-D-009 | DOC-008 AI Engineering Log | Documentation | Should | 7 | 6 | 7 | 1 |  | 5 | To Do | Given DOC-008 → structured log of all AI-assisted engineering decisions Given each entry → task, prompt intent, output, manual changes, outcome | Template generated pre-dev. Filled during development
US-D-010 | Portfolio library page on personal site | Documentation | Should | 8 | 7 | 8 | 4 |  | 5 | To Do | Given portfolio page → all DOC-XXX artefacts listed with download links Given each artefact → one-paragraph annotation explaining the decision it represents Given page → mobile responsive, no login required | Third submission link. High portfolio value
POST-MVP — SHOULD / COULD ITEMS
US-E-001 | Allure Report published to GitHub Pages | Documentation | Should | 6 | 6 | 5 | 3 |  |  | Deferred | Given GitHub Actions → Allure report generated from Playwright results Given GitHub Pages → report published to public URL Given report → becomes fourth submission link | ADR-005. ~30 min post-MVP. Significant portfolio value
US-E-002 | Visual regression baseline + CI comparison | Technical | Should | 5 | 5 | 5 | 3 |  |  | Deferred | Given baseline screenshots committed → Playwright compares on each CI run Given pixel diff above threshold → test fails Given --update-snapshots flag → baseline updated | GL-T-025. Add after UI is stable (Day 4+)
US-E-003 | DORA metrics documentation from GitHub data | Documentation | Should | 7 | 6 | 7 | 2 |  |  | Deferred | Given GitHub Actions logs → Deployment Frequency and Lead Time for Changes calculated Given documented → added to portfolio library as engineering metrics exhibit | GL-T-030. Manual calculation from GitHub Actions run history
US-E-004 | Plasterboard E2E flow (third automated flow) | QA | Could | 5 | 5 | 4 | 2 |  |  | Deferred | Given E2E test 3 → SW1A 1AA → Plasterboard → Separate bag option → skip selection → confirm Given CI → passes alongside E2E test 1 and 2 | Assessment requires minimum 2 flows. Third is bonus.
US-E-005 | Dark mode support | Functional | Won't | 2 | 2 | 1 | 5 |  |  | Deferred | N/A — out of scope for this iteration | Acknowledged. Not forgotten.
US-E-006 | User authentication / login | Functional | Won't | 1 | 1 | 1 | 8 |  |  | Deferred | N/A — assessment explicitly requires no login on demo URL | Out of scope by assessment constraint

## WBS — Functional
Level | Deliverable ID | Deliverable | US Refs | MoSCoW | Day | Effort Est.
1 | F-1 | BOOKING FLOW APPLICATION |  | Must
2 | F-1.1 | Step 1 — Postcode & Address |  | Must | 1
3 | F-1.1.1 | Postcode input + UK validation | US-001 | Must | 1 | 2h
3 | F-1.1.2 | Address lookup API integration | US-002 | Must | 1 | 2h
3 | F-1.1.3 | Address dropdown selection | US-003 | Must | 1 | 1h
3 | F-1.1.4 | Empty state (EC1A 1BB) | US-004 | Must | 1 | 1h
3 | F-1.1.5 | Loading state (M1 1AE, 1500ms) | US-005 | Must | 1 | 1h
3 | F-1.1.6 | Error state + retry (BS1 4DJ) | US-006 | Must | 1 | 2h
3 | F-1.1.7 | Manual address entry fallback | US-007 | Must | 1 | 1h
2 | F-1.2 | Step 2 — Waste Type Selection |  | Must | 2
3 | F-1.2.1 | Waste type radio/card selector (General/Heavy/Plasterboard) | US-008 | Must | 2 | 2h
3 | F-1.2.2 | Plasterboard option branching (3 sub-options) | US-009 | Must | 2 | 2h
3 | F-1.2.3 | POST /api/waste-types on continue | US-010 | Must | 2 | 1h
2 | F-1.3 | Step 3 — Skip Selection |  | Must | 2-3
3 | F-1.3.1 | GET /api/skips with postcode + heavyWaste params | US-011 | Must | 2 | 2h
3 | F-1.3.2 | Skip grid with enabled/disabled states | US-012 | Must | 3 | 3h
3 | F-1.3.3 | Skip selection state + price display | US-013 | Must | 3 | 1h
2 | F-1.4 | Step 4 — Review & Confirm |  | Must | 3
3 | F-1.4.1 | Review summary — all selections displayed | US-014 | Must | 3 | 2h
3 | F-1.4.2 | Price breakdown component | US-014 | Must | 3 | 1h
3 | F-1.4.3 | POST /api/booking/confirm integration | US-015 | Must | 3 | 2h
3 | F-1.4.4 | Double-submit prevention | US-016 | Must | 3 | 1h
3 | F-1.4.5 | Success confirmation screen with bookingId | US-017 | Must | 3 | 1h
2 | F-1.5 | Cross-Cutting UX |  | Must/Should | 2-3
3 | F-1.5.1 | Step navigation (forward + back) with state persistence | US-018 | Must | 2 | 2h
3 | F-1.5.2 | Step progress indicator | US-019 | Should | 3 | 1h
3 | F-1.5.3 | Mobile responsive layout (375px viewport) | US-020 | Must | 3 | 2h

## WBS — Architecture
Level | Deliverable ID | Deliverable | US Refs | MoSCoW | Day | Effort Est.
1 | A-1 | PROJECT ARCHITECTURE LAYERS |  | Must
2 | A-1.1 | Project Setup & Configuration |  | Must | 1 | ~4h
3 | A-1.1.1 | Next.js 14 scaffold + tsconfig + tailwind | US-T-001 | Must | 1 | 1h
3 | A-1.1.2 | GitHub repo + branch protection rules | US-T-002 | Must | 1 | 0.5h
3 | A-1.1.3 | Vercel project + GitHub integration | US-T-004 | Must | 1 | 0.5h
3 | A-1.1.4 | GitHub Projects board setup | US-T-005 | Must | 1 | 0.5h
3 | A-1.1.5 | Playwright config + POM scaffold | US-T-008 | Must | 1 | 1h
2 | A-1.2 | Backend — API Routes (Next.js) |  | Must | 1 | ~8h
3 | A-1.2.1 | POST /api/postcode/lookup + all 4 fixtures | US-T-006 | Must | 1 | 2h
3 | A-1.2.2 | POST /api/waste-types | US-010 | Must | 1 | 0.5h
3 | A-1.2.3 | GET /api/skips + heavyWaste disabled logic | US-T-007 | Must | 1 | 2h
3 | A-1.2.4 | POST /api/booking/confirm + idempotency | US-015 | Must | 1 | 2h
3 | A-1.2.5 | TypeScript types for all API contracts | US-T-001 | Must | 1 | 1h
2 | A-1.3 | Frontend — React Components |  | Must | 1-3 | ~16h
3 | A-1.3.1 | Layout + step wizard shell | US-018 | Must | 1 | 2h
3 | A-1.3.2 | Step 1 component (PostcodePage) | US-001–007 | Must | 1 | 4h
3 | A-1.3.3 | Step 2 component (WasteTypePage) | US-008–010 | Must | 2 | 3h
3 | A-1.3.4 | Step 3 component (SkipSelectionPage) | US-011–013 | Must | 2-3 | 4h
3 | A-1.3.5 | Step 4 component (ReviewPage + ConfirmPage) | US-014–017 | Must | 3 | 3h
2 | A-1.4 | DevOps — CI/CD Pipeline |  | Must | 1 | ~3h
3 | A-1.4.1 | GitHub Actions workflow file | US-T-003 | Must | 1 | 1.5h
3 | A-1.4.2 | Quality gates: tsc + Playwright @smoke | US-T-003 | Must | 1 | 0.5h
3 | A-1.4.3 | Playwright HTML report artefact upload | US-Q-007 | Must | 1 | 0.5h
3 | A-1.4.4 | Vercel production deploy on main merge | US-T-004 | Must | 1 | 0.5h
2 | A-1.5 | QA — Automated Test Suite |  | Must | 4 | ~10h
3 | A-1.5.1 | E2E Flow 1: General waste (chromium) | US-Q-002 | Must | 4 | 2h
3 | A-1.5.2 | E2E Flow 2: Heavy waste + disabled skips | US-Q-003 | Must | 4 | 2h
3 | A-1.5.3 | API tests: all 4 endpoints + error cases | US-Q-004 | Must | 4 | 3h
3 | A-1.5.4 | Accessibility: axe-core per step | US-Q-006 | Must | 4 | 1h
3 | A-1.5.5 | Mobile viewport assertions (375px) | US-020 | Must | 4 | 1h
3 | A-1.5.6 | Lighthouse run + report evidence | US-Q-008 | Must | 4 | 0.5h
2 | A-1.6 | QA — Manual Deliverables |  | Must | 5 | ~6h
3 | A-1.6.1 | manual-tests.md (35+ TCs in markdown table) | US-Q-001 | Must | 5 | 3h
3 | A-1.6.2 | bug-reports.md (3+ structured reports) | US-Q-005 | Must | 5 | 1.5h
3 | A-1.6.3 | ui/ screenshots package (desktop + mobile + states) | US-Q-007 | Must | 5 | 0.5h
3 | A-1.6.4 | Flow video 60–120s | US-Q-007 | Must | 5 | 0.5h
2 | A-1.7 | Documentation Library |  | Must | 1+5 | ~8h
3 | A-1.7.1 | README.md in repo root | US-D-001 | Must | 5 | 1h
3 | A-1.7.2 | DOC-001 through DOC-008 artefacts | US-D-002–009 | Must | 1+5 | Done pre-dev
3 | A-1.7.3 | Portfolio library page on personal site | US-D-010 | Should | 5 | 2h

## DoR & DoD
DEFINITION OF READY (DoR) — Conditions before a US enters development
# | Criterion | Rationale | Gate
1 | US has a unique ID (US-XXX format) and a one-line title | Enables tracking and cross-referencing across all documents | Mandatory
2 | MoSCoW priority is assigned and agreed | Prevents scope creep; ensures correct sequencing | Mandatory
3 | Acceptance Criteria written in Given/When/Then format (minimum 3 AC per US) | Enables unambiguous test case derivation; prevents interpretation gaps | Mandatory
4 | All referenced API endpoints exist in the in-memory fixture layer | No development can proceed if the API contract is missing or unclear | Mandatory
5 | Data-testid attributes planned for all interactive elements in the US | Stable selectors required before Playwright tests can be written | Mandatory
6 | Dependencies on other US identified (e.g. US-003 requires US-002) | Prevents blocked work mid-sprint | Mandatory
7 | Effort estimate provided (hours) | Enables Day-level sprint planning | Mandatory
8 | US is reachable within the current sprint day allocation | Prevents overcommitment in the 5-day timebox | Mandatory
DEFINITION OF DONE (DoD) — Conditions before a US is marked Done
# | Criterion | Rationale | Gate
1 | Feature is implemented and works correctly in the browser (localhost + Vercel preview) | Functional verification before CI | Mandatory
2 | tsc --noEmit passes with zero TypeScript errors | Type safety enforced; contract compliance verified | Mandatory
3 | At least one Playwright test covers the happy path of this US and passes locally | Automation coverage before merge; no untested features | Mandatory
4 | Negative / error cases covered by Playwright test or manual TC (TC-XXX) | Risk-based coverage; not just happy path | Mandatory
5 | GitHub Actions CI pipeline is green (tsc + @smoke tests pass) | Quality gate enforced; no broken main branch | Mandatory
6 | data-testid attributes added to all interactive elements introduced by this US | Stable selectors for future test maintenance | Mandatory
7 | No new console errors or warnings introduced | Code quality signal; catches silent failures | Mandatory
8 | US status updated to Done in GitHub Projects board and DOC-003 Backlog | Single source of truth maintained | Mandatory
9 | If US introduces a new UI component → mobile (375px) layout verified | NFR-004 compliance enforced per feature | Mandatory
10 | If US introduces a new API endpoint → API test (TC-XXX) written and passing | API contract coverage maintained | Mandatory

## Sprint Plan
Day | Focus | US IDs | Key Deliverable | Est. Hours | Done When
1 | Architecture + API + Project Setup | US-T-001, US-T-002, US-T-003, US-T-004, US-T-005, US-T-006, US-T-007, US-T-008 | All 4 API routes with fixtures working · GitHub Actions pipeline green · Vercel connected · Playwright scaffold ready | ~8h | curl /api/postcode/lookup SW1A1AA returns 12 addresses · CI pipeline shows green checkmark on first PR
2 | Frontend Steps 1 & 2 + API integration | US-001, US-002, US-003, US-004, US-005, US-006, US-007, US-008, US-009, US-010, US-018 | Step 1 fully functional (postcode, lookup, empty, loading, error, retry, manual entry) · Step 2 with plasterboard branching | ~9h | Complete Step 1 → Step 2 journey works in browser for all 4 postcodes · Back navigation preserves state
3 | Frontend Steps 3 & 4 + cross-cutting UX | US-011, US-012, US-013, US-014, US-015, US-016, US-017, US-019, US-020 | Skip selection with disabled logic · Review with price breakdown · Confirm with double-submit prevention · Mobile responsive · Progress indicator | ~9h | Full booking flow works end-to-end in browser · Heavy waste disables correct skips · Mobile 375px no overflow
4 | QA — Automation + Lighthouse + Screenshots | US-Q-002, US-Q-003, US-Q-004, US-Q-005 (partial), US-Q-006, US-Q-007, US-Q-008 | Playwright E2E flows 1+2 passing in CI · API test suite complete · Accessibility scan clean · Lighthouse ≥85 · Screenshots + video | ~9h | GitHub Actions CI green on main · All @smoke and @regression pass · Lighthouse report saved · ui/ directory with all required screenshots
5 | QA Manual + Documentation + Submission | US-Q-001, US-Q-005 (complete), US-D-001, US-D-007, US-D-009, US-D-010 | 35+ manual TCs in manual-tests.md · 3+ bug reports · README.md complete · DOC-006 Release Plan · Portfolio library page · Final submission review | ~8h | All assessment checklist items verified against PDF · Three links working: demo + GitHub + portfolio library · README submitted