## README
DOC-008 — AI Engineering Log
REM Waste — Booking Flow Platform · Version 1.0
Document ID | DOC-008
Title | AI Engineering Log
Project | REM Waste Booking Flow Platform
Version | 1.0
Status | Complete
Author | Evgenii Subbotin
Date | 2026-04-17
AI Engine | Claude Code (Anthropic)
References | DOC-001 GL-T-001 · DOC-004 ADR-006 · CLAUDE.md
Purpose & How to Read This Document
This log records every significant AI-assisted engineering decision made during the development of the REM Waste Booking Flow Platform. It demonstrates professional AI-augmented engineering practice: Claude Code was used as an accelerator, not a replacement for engineering judgment. Every entry documents what was requested, what was generated, what was changed manually, and what the outcome was. Governance rule (ADR-006): No AI-generated code was committed without engineer review. All generated tests were executed locally before commit. Failures and corrections are logged honestly — they are evidence of the verification process, not failures of the approach.
Outcome Legend
✅ Accepted as-is | AI output used directly with no changes. Verified by running tests/tsc.
✏️ Accepted with edits | AI output used as base; engineer modified logic, selectors, or structure.
🔄 Iterated | Multiple prompts required to reach acceptable output. Final version accepted.
❌ Rejected | AI output not used. Engineer wrote from scratch or used different approach.
Sheet Guide
Engineering Log | All AI-assisted tasks chronologically. Main reference sheet.
Metrics Summary | Aggregate statistics: tasks by outcome, category, day.
README | This page — purpose, legend, sheet guide.

## Engineering Log
LOG-ID | Day | Category | US / ADR Ref | Task | Prompt Intent | AI Output Summary | Manual Changes Applied | Outcome | Verification Method | Time Saved Est. | Notes / Learning
DAY 1 — Architecture, API Routes, Infrastructure
LOG-001 | 1 | Types & Interfaces | ADR-001 | Create lib/types.ts with full API contract types | Generate TypeScript interfaces for all 4 API request/response types, BookingState, and domain enums based on assessment PDF contract | Generated complete types.ts with all interfaces. Included PlasterboardOption union type, BookingStep numeric literal type, and ManualAddress interface. | Added disabledReason?: string to Skip interface — not in original assessment contract but needed for UI tooltip. Added LoadingState union type. | ✏️ Edited | tsc --noEmit passed with zero errors | 45 min | AI correctly inferred that disabled skips need a reason string even though assessment PDF didn't specify it
LOG-002 | 1 | API Fixture | US-T-006 | Create fixtures/postcodes.ts with all 4 deterministic fixtures | Implement in-memory postcode fixtures: SW1A 1AA (12 addresses), EC1A 1BB (empty), M1 1AE (1500ms delay), BS1 4DJ (500 on first call, 200 on retry). Include module-level counter for BS1 4DJ. | Generated fixtures with all 4 postcodes. Used module-level let counter for BS1 4DJ retry simulation. Included resetBs14djCounter() export. | Changed counter reset strategy: original used Map keyed by request ID which didn't reset between test runs. Replaced with simple module-level number. Added getBs14djResponse() helper to encapsulate counter logic. | ✏️ Edited | Manual curl test: first call returned 500, second returned 200 | 30 min | Counter isolation between test runs is a subtle requirement — AI's Map approach was clever but wrong for module-level state
LOG-003 | 1 | API Fixture | US-T-007 | Create fixtures/skips.ts with 8 sizes and heavyWaste disabled logic | Generate skip options array with 8 sizes (2yd to 16yd), prices, and logic to disable 12yd/14yd/16yd when heavyWaste is true. Include disabledReason string. | Generated getSkips(heavyWaste: boolean) function returning mapped array. Clean implementation with HEAVY_WASTE_DISABLED_SIZES constant. | No changes needed. Exactly matched spec. | ✅ Accepted | Unit tested via curl GET /api/skips?heavyWaste=true — 3 skips had disabled:true | 20 min
LOG-004 | 1 | API Route | US-T-006 | Implement POST /api/postcode/lookup route handler | Next.js App Router route handler for POST /api/postcode/lookup. Implement UK postcode validation regex, fixture lookup, M1 1AE latency simulation, BS1 4DJ retry counter, error responses (400/422). | Generated route.ts with full implementation. Correct status codes. Used NextResponse.json(). Included regex validation. | Fixed postcode normalisation: AI stripped spaces before regex check but kept spaces in response. Standardised to normalise after validation. Added explicit 405 for non-POST methods. | ✏️ Edited | curl tests for all 4 fixtures + invalid inputs. All returned correct status codes. | 40 min | Postcode normalisation order matters: validate with spaces, strip for comparison, return original format in response
LOG-005 | 1 | API Route | US-010 | Implement POST /api/waste-types route handler | Simple route handler. Validate that if plasterboard:true then plasterboardOption must not be null. Return {ok: true} on success. | Generated clean implementation with correct validation logic. | No changes. | ✅ Accepted | curl with plasterboard:true + null option returned 400. Valid payload returned {ok:true} | 10 min | Simplest of the 4 routes — AI nailed it first time
LOG-006 | 1 | API Route | US-011 | Implement GET /api/skips route handler | GET handler with postcode and heavyWaste query params. Call getSkips() fixture. Return {skips: [...]}. | Generated handler using searchParams. Correct response shape. | Added type coercion for heavyWaste: URL params are strings, needed explicit === 'true' comparison rather than Boolean() coercion. | ✏️ Edited | curl GET /api/skips?postcode=SW1A1AA&heavyWaste=true — correct disabled skips returned | 15 min | Boolean coercion from URL query strings is a classic gotcha — AI used Boolean() which treats 'false' as truthy
LOG-007 | 1 | API Route | US-015 | Implement POST /api/booking/confirm route handler | Validate all required fields present. Generate random bookingId (BK- + 5 digits). Return {status:'success', bookingId}. | Generated with field validation and random ID generation using Math.random(). | Changed ID generation to zero-padded 5 digits for consistent format: BK-12345 not BK-1234 or BK-123456. | ✏️ Edited | curl POST with valid payload returned {status:'success', bookingId:'BK-XXXXX'} | 15 min
LOG-008 | 1 | DevOps | US-T-003 | Create .github/workflows/playwright.yml | GitHub Actions workflow: checkout, setup Node 24, npm ci, tsc --noEmit, playwright install, smoke tests on PR, full regression on push to main, upload artifacts. | Generated complete workflow. Correct job structure. Artifact upload with retention. | Updated Node version from 20 to 24 after deprecation warning. Added explicit timeout-minutes: 20. Fixed BASE_URL env variable syntax. | ✏️ Edited | Pipeline ran green on first push after fixes | 20 min | Node 24 deprecation warning required two iterations to resolve — GitHub Actions runtime vs app runtime are separate concerns
DAY 2 — Frontend Steps 1 & 2
LOG-009 | 2 | Component | US-019 | Create StepIndicator component | Responsive step progress indicator showing steps 1-4. Current step highlighted, completed steps with checkmark, future steps inactive. data-testid on each step. | Generated clean Tailwind component with correct visual states. | No structural changes. Adjusted colour tokens to match project palette (blue-600 not blue-500). | ✏️ Edited | Visual check in browser at 375px and 1024px | 15 min
LOG-010 | 2 | Component | US-001 | Create Step1Postcode component — full implementation | Complex component: postcode input with validation, API call, address list display, empty state, loading state, error+retry state, manual entry toggle. All data-testid attributes per CLAUDE.md spec. | Generated ~200 line component. All states implemented. Correct data-testid naming. UK postcode regex included client-side. | Three significant changes: (1) Loading state didn't disable the input — added disabled prop. (2) Error message wasn't accessible — added role='alert'. (3) Manual entry form was hidden with CSS display:none — changed to conditional render for proper DOM presence. | ✏️ Edited | Playwright @smoke test passed. axe-core scan: zero violations on Step 1. | 90 min | Accessibility issues (role=alert, disabled inputs) are the most common AI blind spot in form components
LOG-011 | 2 | Component | US-008 | Create Step2WasteType component with plasterboard branching | Three waste type cards (General/Heavy/Plasterboard). When Plasterboard selected, show 3 sub-options. API call on Continue. All data-testid attributes. | Generated component with branching logic. Cards with correct selection states. | Fixed state management bug: changing waste type from Plasterboard to Heavy didn't clear plasterboardOption. Added useEffect to clear option on type change. | ✏️ Edited | Manual test: select Plasterboard → select option → change to Heavy → back to Plasterboard → option was cleared. Confirmed. | 45 min | State clearing on type change is exactly the kind of edge case assessors look for — became BUG-001 in bug reports
LOG-012 | 2 | State | US-018 | Create BookingWizard orchestrator component | Top-level wizard component managing currentStep state and BookingState. Renders correct step component. Passes state down and callbacks up. Back navigation preserves state. | Generated clean orchestrator. Correct useState pattern. Prop drilling to step components. | Added waste type change guard: when going back to Step 2 and changing waste type, clear selectedSkip. Without this, a heavy-waste-incompatible skip could persist to review. | ✏️ Edited | Manual flow test: full booking, back navigation, waste type change — all state transitions correct. | 30 min
DAY 3 — Frontend Steps 3 & 4
LOG-013 | 3 | Component | US-012 | Create SkipCard component with enabled/disabled states | Individual skip card showing size, price, availability. Disabled state: greyed out, not clickable, reason tooltip. Selected state: blue border highlight. | Generated card with all three visual states. Correct Tailwind classes. | Added aria-disabled='true' on disabled cards and aria-pressed on selected cards for accessibility. Added keyboard handler (Enter/Space to select) — AI only implemented onClick. | ✏️ Edited | axe-core scan clean. Keyboard navigation test: Tab to card, Enter to select — worked. | 25 min | Keyboard accessibility for custom interactive elements is consistently missed by AI — always check
LOG-014 | 3 | Component | US-011 | Create Step3SkipSelect with API fetch and grid layout | Fetch skips on mount, render SkipCard grid, handle selection, show selected summary with price. Responsive: 1 col mobile, 2 col tablet, 3-4 col desktop. | Generated with useEffect fetch, loading state, grid layout. | Fixed two issues: (1) heavyWaste wasn't being passed to API query — had to thread it through from BookingWizard. (2) Postcode normalisation before API call was missing — API expects no spaces. | ✏️ Edited | Heavy waste flow: 12yd and 14yd showed disabled. 8yd selectable. Price summary updated on selection. | 40 min | Props threading through multiple component levels is where AI loses context — always verify data flow end-to-end
LOG-015 | 3 | Component | US-014 | Create Step4Review with price breakdown and confirm | Full booking summary. Price breakdown section. Confirm button with double-submit prevention. Loading state. Success screen with bookingId. | Generated complete review component. Price breakdown table. Disabled-on-click pattern for double submit. | Double-submit prevention had a race condition: button was disabled in React state but second click could fire before re-render. Added ref-based guard: const submitting = useRef(false) checked before any API call. | ✏️ Edited | Playwright double-submit test: two rapid clicks → only one POST fired. Verified via request intercept count. | 50 min | useRef for imperative guards is the correct pattern for preventing race conditions — React state alone is insufficient
DAY 4 — Test Automation
LOG-016 | 4 | Page Object | ADR-004 | Generate all 4 Page Object classes | Create Step1PostcodePage, Step2WasteTypePage, Step3SkipSelectPage, Step4ReviewPage extending BasePage. Locators as class properties using getByTestId. | Generated all 4 classes following BasePage pattern. Clean locator definitions. | Minor: added skipCard(size) method to Step3 as dynamic locator factory — AI had hardcoded individual skip locators. | ✏️ Edited | POM classes imported in tests — no import errors | 20 min
LOG-017 | 4 | E2E Test | US-Q-002 | Generate general waste E2E flow spec | Complete @smoke test: SW1A 1AA → select address → General waste → 6-yard skip → review check → confirm → bookingId visible. Assert each step. | Generated test with correct flow. Assertions at each step. @smoke tag. | Fixed selector for bookingId display — AI used getByText(/BK-/) but the element needed getByTestId('booking-id'). Added assertion for price breakdown visibility. | ✏️ Edited | Test passed locally: chromium 45s. CI: green. | 30 min
LOG-018 | 4 | E2E Test | US-Q-003 | Generate heavy waste E2E flow spec | Complete @smoke test: SW1A 1AA → Heavy waste → assert 12yd and 14yd disabled and not clickable → select 8yd → confirm. | Generated test. Correct disabled assertions. | Added assertion that disabled skips have aria-disabled='true' — not just visual check. Added request payload assertion: heavyWaste:true in POST body. | ✏️ Edited | Test passed. Disabled skip assertion caught a bug where 16yd was not visually disabled even though disabled:true in API response. | 25 min | Request payload assertion is more valuable than UI assertion — caught a real rendering bug
LOG-019 | 4 | API Test | US-Q-004 | Generate API test suite for all 4 endpoints | APIRequestContext tests: happy path, missing fields (400), invalid format (422), BS1 4DJ retry sequence, schema validation. | Generated comprehensive API tests. Correct status code assertions. Schema validation pattern. | BS1 4DJ retry test was flaky: module counter state persisted between test runs when running full suite. Added beforeEach hook to reset counter via test-only API endpoint. Created /api/test/reset-fixtures route gated on NODE_ENV !== 'production'. | 🔄 Iterated | After 3 iterations: all API tests pass consistently. No flakiness in 10 sequential runs. | 60 min | Test isolation for stateful fixtures is the hardest problem — required a dedicated reset endpoint which itself needed to be secured
LOG-020 | 4 | A11y Test | US-Q-006 | Generate accessibility tests with axe-core | axe-core scan on each step page. Assert zero critical/serious violations. Keyboard navigation test. Touch target size assertions. | Generated tests with @axe-core/playwright integration. | No code changes. One genuine accessibility bug found: Step 3 skip grid had no visible focus indicator on keyboard navigation. Fixed in Step3SkipSelect component (added focus:ring-2 Tailwind class). | ✅ Accepted | axe-core: zero violations on all steps. Keyboard nav: all elements reachable. | 20 min | AI-generated a11y tests found a real bug that manual testing missed — demonstrates value of automated accessibility coverage
LOG-021 | 4 | Visual | US-Q-007 | Generate mobile viewport assertions | Playwright test at 375px viewport: no horizontal overflow, touch targets ≥ 44px, full flow usable. | Generated viewport tests. Correct scrollWidth assertion pattern. | Added specific touch target assertion for Confirm button — was 38px height on mobile. Fixed in component with explicit py-3 → py-4 class change. | ✏️ Edited | Mobile viewport test: all assertions pass. 375px no overflow confirmed. | 20 min
DAY 5 — Documentation & Submission
LOG-022 | 5 | Documentation | US-Q-001 | Generate manual-tests.md structure and first 20 TCs | Markdown table format with columns: TC-ID, Title, Preconditions, Steps, Expected Result, Actual Result, Status, Priority. Generate 20 test cases covering happy path and main negative cases. | Generated 20 TCs in correct markdown table format. Good coverage of postcode validation and API error cases. | Engineer wrote remaining 15 TCs manually — edge cases for plasterboard branching, state transitions, and double-submit scenarios that required domain knowledge of the specific implementation. | ✏️ Edited | Reviewed for format compliance against assessment PDF requirements | 90 min | AI handles systematic test generation well but misses implementation-specific edge cases that require knowing the code
LOG-023 | 5 | Documentation | US-D-001 | Generate README.md structure | README with all required sections: demo URL, repo URL, portfolio URL, local setup, test data strategy, AI engineering approach, doc library links. | Generated complete README structure with all sections. | Rewrote 'AI Engineering Approach' section in first person — AI-generated text was too generic. Added specific examples from DOC-008. Engineer added personal reflection on the AI-first workflow. | ✏️ Edited | Visual review — all links present, setup instructions tested | 30 min | README is the cover letter — the personal voice section must be written by the engineer, not generated
LOG-024 | 5 | Documentation | US-D-009 | Generate DOC-008 AI Engineering Log (this document) | xlsx document with all AI-assisted decisions logged, metrics summary, and evidence of AI governance process. | Generated complete log with all entries from days 1-5. | Engineer reviewed all entries for accuracy and added specific technical details that Claude Code couldn't know (exact line numbers changed, specific bugs found, time estimates). | ✏️ Edited | Self-referential — verified all LOG-IDs are sequential and categories are consistent | 45 min

## Metrics Summary
DOC-008 — AI Engineering Log: Metrics Summary
OUTCOME DISTRIBUTION — 24 Total AI-Assisted Tasks
Outcome | Count | Percentage | Interpretation
✅ Accepted as-is | 4 |  | Used directly — zero manual changes required
✏️ Accepted with edits | 16 |  | AI output as base; engineer improved/fixed
🔄 Iterated | 1 |  | Required multiple prompts to reach acceptable output
❌ Rejected | 0 |  | Not used — engineer wrote from scratch
TOTAL
TASKS BY DAY
Day | Focus | Tasks | Est. Time Saved | Key Outcome
1 | Architecture + API + Infrastructure | 8 | ~3h | All 4 API routes working. CI pipeline configured.
2 | Frontend Steps 1 & 2 | 4 | ~3h | Step1 a11y bug found + fixed. Plasterboard state bug identified.
3 | Frontend Steps 3 & 4 | 3 | ~2.5h | Double-submit race condition found + fixed with useRef.
4 | Test Automation | 6 | ~3h | Fixture isolation bug found. Real a11y bug caught by automated scan.
5 | Documentation | 3 | ~2.5h | This document generated + reviewed.
TOTAL |  |  | ~14h
KEY FINDINGS & PATTERNS
Finding | Detail
Most common AI gap | Accessibility — 3 of 4 a11y issues (role=alert, aria-disabled, focus ring) were introduced by AI and caught by engineer review or automated axe-core scan
Most valuable AI contribution | Boilerplate elimination — Types, fixtures, route handlers, and page objects generated in minutes vs hours. Estimated 14h saved across 5 days.
Most complex iteration | LOG-019: BS1 4DJ retry test isolation required 3 prompt iterations and a dedicated test-reset API endpoint
Biggest surprise | AI-generated axe-core tests (LOG-020) caught a real accessibility bug in the skip grid focus handling — automated tests finding bugs in AI-generated code
AI governance outcome | 24 tasks: 0 rejected, 4 accepted as-is (17%), 16 edited (67%), 1 iterated (4%). 100% of output verified before commit.
Pattern identified | AI excels at systematic generation (types, routes, POM classes) but requires engineer intervention for: state management edge cases, accessibility attributes, and test isolation strategies
VERSION HISTORY
Version | Date | Author | Changes
1.0 | 2026-04-17 | Evgenii Subbotin | Initial complete version